## TR-ANZGOG docs - all desired
All TR-ANZGOG documents desired (to be included as links into one document, where possible)
Reviewers | Steering Committee (S/C)
Board (B)
Consensus Workshop (CW)
Data Working Group (DWG)
Consent Working Group (CWG)
Lab Network Working Group (LNWG)
Alison Choy Flanigan (ACF)
Anna de Fazio (AdF)
Alison Evans (AE)
SECTION # | SECTION | SUB-SECTION | DOCUMENT # | DOCUMENT NAME | VERSION # | VERSION DATE | STATUS AT 24 August 2020 | APPROVAL TARGET DATE | COMMENTS | APPROVED BY |  |  | WHO HAS BEEN CONSULTED? | SPECIALIST ADVICE REQUIRED? | [6 empty] | REFERENCES | Make available on ANZGOG website?
[11 empty] | Completion date | Revision due date |  | S/C | AE | AdF | legal (ACF) | WG | RMG | CTC/ BaCT
-1 | Start Up (including Background) | n/a | -1.1 | Workshop Oct 2016: PowerPoint Presentation and Minutes | FINAL | 2016-11-18 | Approved | n/a |  | n/a | 2016-11-18 | n/a | ANZGOG working group | - | - | - | - | - | - | - |  | No
|  | n/a | -1.2 | ASM Presentation 2017 | FINAL | 2018-09-23 | Approved | n/a |  | AdF | 2017-03-30 | n/a | ANZGOG members | - | - | - | - | - | - | - |  | No
|  | n/a | -1.3 | Position Paper; prepared by Dr Helen Gooden 2017 | FINAL AE - HG_AdF_CD | 2018-08-15 | Approved | n/a | Correction of Mater pathologist details | AdF, AE | 2017-09-05 | n/a | broad sector consultation | - | - | - | - | - | - | - |  | No
|  | n/a | -1.4 | Project Timeline | V2.3 | 2020-04-01 | Live document | n/a | Revised to reflect JTR progress report milestone date revision | AE | 2020-04-25 | Quarterly review | AE, AdF | - | - | - | - | - | - | - | JTR, NSWHSB grant applications | No
|  | n/a | -1.5 | Work Breakdown Structure | V1.3 | 2019-11-26 | Approved | n/a | Visio task for planning after Project Management course | AE | 2019-11-26 | n/a | AE | - | - | - | - | - | - | - |  | No
|  | n/a | -1.6 | Scoping Document | V1 | 2020-05-20 | Discovery' document - approval n/a | n/a | Prepared following Project Management course, based upon existing TR-ANZGOG docs and discussions. Is this necessary to describe the scope of TR-ANZGOG or will the 'Protocol' be adequate? Misconceptions such as screening by Tr-ANZGOG etc | not required - Discovery doc | n/a | n/a | AE, ADF | - | - | - | - | - | - | - |  | No
|  | n/a | -1.7 | TR-ANZGOG Consensus Workshop Summary Report | V1 | 2019-12-16 | Approved | n/a | Attendees received Alison Evans Consulting version (with couple of minor changes by CD). | AE | 2019-12-16 | n/a | CW, AE, AdF | - | - | - | - | - | - | - |  | No
1 | TR-ANZGOG Overview | n/a | 1.1 | TR-ANZGOG Protocol | V2_draft | 2020-05-13 | Drafted. Reviewed AE and ADF. To be finalised following completion of other documents which comprise this overarching document | 2020-07-01 | V1.1 drafted June 2019 based upon CTRNet Protocol template. Reviewed AE. Overhauled May 2020. Reviewed AE & ADF. | pending | pending |  | AE, ADF | Yes | Yes | Yes | Yes | - | - | - | CTRNet template initially. | ?
2 | Principles | n/a | 2.1 | Key Principles | V1.7_draft | 2020-05-20 | Awaiting SC approval | 2020-07-01 | Board had approved July 2019. Amended following consensus workshop feedback. Emailed to SC for approval | pending | pending | pending | Board, CW, S/C | Yes | - | - | - | - | - | - | Position paper, B, CW | Yes
3 | Governance | n/a | 3.1 | Governance Reporting Structure | v1.7_draft | 2020-05-26 | Awaiting SC approval | 2020-07-01 | Amended to combine 2 subcommittees as per Board recommendations. Emailed to SC for approval | Board (with combined subcommittes) | pending | pending | S/C, B, CW | Yes | - | - | - | - | Yes? | - |  | Yes
|  | TOR | 3.2.1 | TOR - TR-ANZGOG Steering Committee | V1.2 | 2019-01-31 | Approved | n/a | Due for review S/C meeting Sep 2020 | S/C | 2019-02-01 | 2021-02-01 | S/C | - | - | - | - | - | - | - | TTWG TOR | No
|  | TOR | 3.2.2 | TOR- TR-ANZGOG Trial Support and Sample Access Committee | V1.2_draft | 2020-05-26 | Awaiting SC approval | 2020-07-01 | GynaeBiobank doesn't have TOR. NSWHSB Access committee TOR referenced | pending | pending | pending | S/C | Yes | - | - | - | - | - | - | S/C TOR, NSWHSB Access committee TOR | No
4 | Ethics and Consent | Policies | 4.1.1 | Ethically Defensible Plan | V1_Draft (see comments) | 2018-12-05 | Approved | n/a | Sent to S/C members prior to NSWHSB Grant submission. Circularized at Consensus Workshop. (labelled draft for NSWHSB submissions purposes but no amendments suggested by Consensus workshop) | AdF | 2018-12-01 | 2022-07-01 | SC, CW | - | - | - | - | - | - | - | INOVATe? | Yes
|  | Templates | 4.2.1 | Trial-specific Participant Information Coversheet | V1.2_clean | 2020-05-22 | Approved | 2020-07-01 | New template based upon NSWHSB Consent Toolkit resource circularized April 2020. Typo in V1 corrected | CWG | 2020-06-09 | 2022-07-01 | NSWHSB template, CWG | - | - | - | - | - | - | - | NSWHSB, | Yes
|  | Templates | 4.2.2 | TR-ANZGOG Biobanking Participant Information Sheet | V1_clean | 2020-07-23 | Approved | 2020-07-01 | Amended as per workshop, working group (V1.5 20/2/20); prior to new NSWHSB-issued template. NSWHSB template sent to CWG and amended following AdF & SB feedback. Amendments approved AdF 23July2020. | CWG | 2020-07-23 | 2022-07-01 | CWG, CW, NSWHSB template | - | - | - | - | - | - | - | NSWHSB, NHMRC | Yes
|  | Templates | 4.2.3 | TR-ANZGOG Biobanking Participant Consent Form | V1_clean | 2020-05-22 | Approved | 2020-07-01 | NSWHSB template amended to specify Biobanking consent (V1.2 28/1/2020). Logo added 21/8/2020 | CWG | 2020-06-09 | 2022-07-01 | CWG, CW, NSWHSB template | - | - | - | - | - | - | - | NSWHSB, NHMRC | Yes
|  | Templates | 4.2.4 | TR-ANZGOG Biobanking Consent Withdrawal Form | V1 | 2020-01-29 | Approved | n/a | No withdrawal form template found on NSWHSB site. Based upon NHMRC template. No amendments suggested. Header for version details added 24Aug2020 | CWG | 2020-01-01 | 2022-07-01 | CWG, CW | - | - | - | - | - | - | - | NHMRC | Yes
|  | Templates | 4.2.5 | FAQ: TR-ANZGOG, Biobanking and the NSW Health Statewide Biobank | V1_clean | 2020-07-24 | Approved | 2020-07-01 | New resource by NSWHSB tweaked for TR-ANZGOG. Reviewed by CWG. Amendments suggested by SB and AdF. Approved AdF 24/7/2020. | CWG | 2020-07-24 | 2022-07-01 | CWG, NSWHSB template | - | - | - | - | - | - | - | NSWHSB | Yes
|  | Templates | 4.2.6 | Clinical Trial PIS: TR-ANZGOG Reference Text | V1.6_clean | 2020-05-22 | Approved | 2020-07-01 | Given the NSWHSB templates, the Biobanking aspect of TR-ANZGOG is now a separate PIS. This text is for inclusion in to the trial PIS | CWG | 2020-06-09 | 2022-07-01 | CWG, CW | - | - | - | - | - | - | Yes? | NHMRC
|  | Templates | 4.2.7 | TR-ANZGOG wording for trial Protocol inclusion | V1_Draft | 2020-08-21 | Awaiting AE/ AdF/ JA/ RP feedback 21/8/2020 | 2020-09-04 |  | pending | pending | pending | AE, JA | - | Yes | Yes | - | - | - | Yes?
5 | TR-ANZGOG Laboratory Network | Policies | 5.1.1 | Expression of Interest request | V1.4_clean | 2020-02-20 | Approved | 2020-07-01 | Lab WG approved, with more detail included re publication acknowledgement vs authorship. Letter requires AdF and AE signature | LNWG (with publication detail) | pending- requires AE, ADF signature | n/a | LNWG | - | Yes | Yes | - | - | - | - |  | Yes
|  | Policies | 5.1.2 | Cost recovery policy | V2_clean (not marked final as 'live' document) | 2020-05-24 | Approved | 2020-07-01 | LNWG approval 24May2020 | LNWG | 2020-05-24 | Quarterly review? | AE, AdF, LNWG, HCB | - | - | - | - | - | - | - | INOVATe, kConFab, NSWHSB, APGI, Griffith, Mater Path, TRI, WIMR | Yes
|  | Policies | 5.1.3 | Approval as TR-ANZGOG Network laboratory process | V1.5_draft | 2020-08-21 | Approved | 2020-07-01 | Currently includes as appendices the application form and review form (based onFNR scoring sheet). Ensure includes sign off by Research Management Group and TR-ANZGOG SC Chair | LNWG, ADF. Obtain RMG approval too | 2020-08-21 | review after testing process with a few labs | AE, AdF, LNSWG | - | - | - | - | - | Yes | - | GCIG | Yes
|  | Policies | 5.1.4 | CRA overarching between ANZGOG and institute | SOLACE2_Master template_for labs provided to ACF | pending | Quote approved AE. Awaiting ACF review 3/8/2020 | 2020-07-01 | SOLACE2 TR CRA amended for TR-ANZGOG. Provided to ACF with request to include reference to publication policy, cost recovery model, processing requirements and QC/ QA requirements eg. emergency response freezer breakdown etc ACF suggested new doc might be required, including MTA-type wording | pending | pending | 2 yearly? | AE, ADF, LNWG, ACF | - | Yes | Yes | Yes | - | - | - | ANZGOG FNR, SOLACE2, PRECISE, BaCT CRAs, CTRNet QC/QA docs | No
|  | Policies | 5.1.5 | Sub study agreement schedule template | Pending from ACF | Pending | Quote approved AE. Awaiting ACF review 3/8/2020 | 2020-07-01 | trial specific. Paragon example available but still in depth. Use PIS coversheet for template?? | pending | pending | 2 yearly? | AE, ADF, LNWG, ACF | - | Yes | Yes | Yes | - | - | - | SOLACE2, NSWHSB, PARAGON sub-study | No
|  | SOP | 5.2.1 | Biospecimen Processing Manual | V1.3_draft | 2020-08-18 | Awaiting feedback LNWG 18/8/2020 | 2020-07-17 | Feedback received LNWG 8/7. Further amendment needed but otherwise approved (Ascites to be reviewed so flexible, efficient, flow chart for downstream processing as required). Ascites section greatly changed so LNWG review requeste | pending | pending | 2 yearly? | AE, LNWG | - | - | Yes | - | Yes | - | - | AOCS, INOVATe, (ICON7, kConFab) | No
|  | SOP | 5.2.2 | LIMS data entry instructions | pending LIMS system | n/a | Software provider inclusion | 2020-12-01 | Should be provided by LIMS company as part of training. | n/a | pending | n/a | To be provided by LIMS company | - | - | - | - | - | - | - |  | No
|  | Templates | included in 5.1.3 | Application form for participation as TR-ANZGOG Network Laboratory | included as Appendix A in Approval process policy | 2020-06-23 | Approved | 2020-07-01 | Approved AdF 24/7/2020. Test with just a couple of labs first before all. | refer 5.1.3 | refer 5.1.3 | refer 5.1.3 | refer 5.1.3 | - | - | - | - | - | - | - |  | Yes
|  | Templates | included in 5.1.3 | TR-ANZGOG Network Laboratory - Assessment Form | Included as Appendix B in Approval process policy | 2020-05-24 | Approved |  |  | refer 5.1.3 | refer 5.1.3 | refer 5.1.3 | refer 5.1.3 | - | - | - | - | - | - | -
|  | Templates | 5.3.1 | List of participating labs/ biobanks | V1_draft | 2020-02-07 | Pending agreements with labs; S/C members to provide recommendations | 2020-12-01 | Labs approached for preliminary discussion: WIMR, NSWHSB, AOCS, WEHI, VCBB, Mater Research, Pam Pollock, WAGO, SACRB, Uni Adelaide, HCB, Griffith, OCRF (Hudson). Awaiting recommendations from SC prior to progressing | pending | pending | Annual review? | AE, AdF, LNWG, S/C | Yes | - | - | - | - | - | - |  | Yes
6 | Clinical Trial Support Resources | Policy | 6.1.1 | Recommended Biospecimen Collection | V1.2_draft | 2020-05-24 | Awaiting SC approval | 2020-07-01 | feedback from CW incorporated and combined with 'Biospecimen Acquisition draft 12May' (CTRnet protocol template) outlining collection methods | pending | pending | 2 yearly? | AE, AdF, SC, Board, CW | Yes | - | - | - | - | - | - |  | Yes
|  | Policies | ANZGOG doc | ANZGOG Publication policy | Text from TR-ANZGOG Key Principles inserted into ANZGOG doc | Feb 2019 edits' | Approved | 2020-07-01 | Text taken from TR-ANZGOG Key Principles and inserted into ANZGOG Publication Policy. AOCS policy received 25/6/20 - emailed to JA, AE, RP. Current wording consistent with AOCS' | JA | 2020-06-25 | 2 yearly? | AE, LNWG, SC, CW | - | - | - | - | - | - | - | SOLACE2 CRA publication policy text, RAC, AOCS | Yes
|  | Agreements | 6.2.1 | CRA - Trial investigators ("Investigator Agreement") | Proposed wording sent to JA/AE/RP 21/8/2020 for inclusion in ANZGOG agreement | 2020-08-21 | Awaiting AE/ JA/ RP feedback 21/8/2020 (ADF required?) | 2020-09-04 | CD additions to iPRIME (Meniawy_ANZGOG Study Chair Agreement Draft 21 December 2017 (002)_JA Ed.._CD) | pending | pending | 2 yearly? | AE, JA, ADF | - | Yes | Yes | Yes? | - | yes? | - | SOLACE2, iPRIMe | No
|  | Agreements/ Template | 6.2.2 | MTA-style pathology agreement for FFPE access/ "Block request from pathology labs" | V1_draft (combined approach) | 2020-08-28 | In progress | Aug 2020 | Provided by Prof Peter Watson. BC version has waiver of consent from participants and different mode of tissue collection and payment. CTRNet example amended for TR-ANZGOG but different mechanisms. CD to review in conjunction with ICON9 request, Sue Brew's template and SOLACE2 BSM and letter to pathologists | pending | pending | 2 yearly? | AE, Clare Scott, Prof Peter Watson, CW pathologists | - | Yes | Yes | - | - | - | - | Provided by Peter Watson | No
|  | Templates |  | Tissue shipment form (sites/ pathology departments to central lab) | V1_draft | 2020-08-28 | In progress | 2020-10-01 | Use SOLACE2 BSM appendix as template (refer also ICON9 and CTRNet) Include permission for retention of block and TMA construction. Incorporate tissue sample requirements (Sue Brew and SOLACE2)
|  | Templates |  | Sample tracker | V1_draft | 2020-08-28 | In progress | 2020-10-01 | ICON9 tweaked
|  | Templates | 6.3.1 | TR-ANZGOG Clinical Trial Support Application Form | V1.1 | 2019-06-06 | In progress | Aug 2020 | Needs more detail re the extent of specimen collection - refer NSWHSB application form | pending | pending | -: Yes; Yes: Yes; Yes: Yes; -: -; -: - | WIMR, See NSWHSB collection form | Yes
|  | Templates | 6.3.2 | TR-ANZGOG Clinical Trial Support Review Form | pending | Pending | In progress | Aug 2020 | Can FNR format be tweaked for this? | pending | pending | -: Yes; Yes: Yes; Yes: Yes; -: -; -: - |  | No
|  | Templates | 6.3.3 | Site Biospecimen Sampling Manual | V1.1 | 2019-09-06 | Template to be updated (SOLACE2) and INOVATE | Aug 2020 | SOLACE2 used as a template | pending | pending |  | SOLACE2 PIs and scientists, CTC, Sites | - | - | - | - | - |  |  | Other ANZGOG clinical trial lab manuals, Sonic lab manual | Upon request
|  | Templates | 6.3.4 | Site Initiation Visit slides | V1.1 | Pending | Template to be updated (SOLACE2) | Aug 2020 | Use SOLACE2 as a template | pending | pending | LNWG: SOLACE2 PIs and scientists, CTC, Sites; -: -; Yes: -; Yes: -; -: - | SOLACE2 | Upon request
|  | Resources | 6.4.1 | Trial budget guidance | Refer Cost recovery policy - TR-ANZGOG Lab network:V2_Final | 2020-05-24 | Budget to be prepared in consultation with Sponsor/ Operating centre | Aug 2020 | Use AdF's grant application example and cost recovery model for TR-ANZGOG labs. Provide guidance over pathology fees | pending | pending |  | AdF | - | Yes | Yes | - | - |  |  | WIMR grant, CTRNet online tool, external pathology and biobank labs | Upon request
|  | Resources | 6.4.2 | Analyte requirements overview | n/a | n/a | Future opportunity |  | Compile list as requests come in - Live document. Check with Cath Kennedy/ Pam the usual queries | pending | pending |  | NSWHSB | - | Yes | Yes | - | Yes |  |  | ISBER, ABNA | Upon request
|  | Agreements | n/a | Draft letter to PIs for trials in development (from PB) | draft | 2020-07-30 | Awaiting approval from AE | 2020-10-01 | To be addressed to Chee Lee, Linda Mileshkin, Rhonda Farrell, as PIs for trials in development to commence TR-ANZGOG | pending | pending | n/a | n/a | - | Yes | - | - | - | Yes (PB) | - | n/a | No
7 | Data Management | Policy | 7.1.1 | Data policy (& Data sharing agreement) | pending | Pending | Requires further input for development from management and DMWG | Sept 2020 | Seek Data WG assistance - transfer of what data, what format etc. Refer feedback from consensus workshop | pending | pending |  | CW | Yes | Yes | Yes | Yes | Yes |  |  | CTRNet | Upon request
|  | Policy | 7.1.2 | Essential data collection requirements | V1.3 | 2020-05-25 | Requires amendment following Penny Webb's feedback but otherwise approved. Align with INOVATe CRF timepoints | Sept 2020 | Refine as per Data WG suggestions re timing of trial ie. diagnosis or recurrence | pending | pending |  | AE, DWG | - | - | Yes | - | Yes |  |  | AOCS, INOVATe, publications, | Upon request
|  | Policy | 7.1.3 | Longitudinal follow up of patient outcomes process | n/a | n/a | Future opportunity | Sept 2020 | Build into model as recommended by AE, C.Scott, DWG. Contact made with NGOR re collaboration - supportive | pending | pending |  | AE, AdF, NGOR | Yes | Yes | Yes | - | Yes |  |  | NGOR collab. Other? | No
8 | Privacy and Security | Policy | ANZGOG doc | Data breach and response plan | Current ANZGOG version | TBC | ANZGOG policy available | n/a | CTRnet also have templates | n/a | n/a |  | ANZGOG doc | - | - | - | Yes | - |  |  | ANZGOG current policy. Refer CTRnet if required | No
|  | Policy | ANZGOG doc | Confidentiality Disclosure Agreement Template | Current ANZGOG version | TBC | ANZGOG policy available | n/a | CTRnet also have templates | n/a | n/a |  | ANZGOG doc | - | - | - | Yes | - |  |  | ANZGOG current policy. Refer CTRnet if required | No
|  | Policy | ANZGOG doc | Code of conduct and ethics, incorporating confidentiality agreement | Current ANZGOG version | TBC | ANZGOG policy available | n/a | CTRnet also have templates | n/a | n/a |  | ANZGOG doc | - | - | - | Yes | - |  |  | ANZGOG current policy. Refer CTRnet if required | No
|  | SOP | 8.2.1 | Destruction of data and samples checklist | pending | Pending | Template to be updated - OBER (review CTC version too) | Sept 2020 | Tweak CTRnet template for TR-ANZGOG | pending | pending | -: -; Yes: Yes; Yes: Yes; -: -; -: - | CTRNet | No
9 | Biospecimen and Data Access & Release | Policy | 9.1.1 | Biospecimen and Data access and release policy | V1.5 | 2020-09-09 | Awaiting SC approval | Sept 2020 | Flowchart V1.4 approved by Board (with HREC approval at start). Amended following Board and Consensus workshop feedback. Updated for formatting and font only 09Sept2020 | pending | pending |  | S/C, Board, CW | Yes | Yes | Yes | Yes | - |  |  | AOCS, NSWHSB, APGI, INOVATe, WIMR, VCB, Griffith Uni Biobank, publications | Yes
|  | Policy | 9.1.2 | Universal Biobanking MTA | Stafford Fox version? Canadian Network's? | Pending | Template to be confirmed | Sept 2020 | Clare Scott provided GCIG template (via SFRC) of Universal MTA template. Does ANZGOG have one already? See also CTRNet, NSHWSH | pending | pending |  | Clare Scott | Yes | Yes | Yes | Yes | - |  |  | GCIG (via SFRC), NSWHSB, AOCS, Alfred Health VIC | Yes
|  | SOP | 9.2.1 | Biospecimen and data transfer | pending | Pending | Requires further input for development from management and DMWG | Sept 2020 | CTRnet template for shipping. Data sharing needs input from DWG/ CTC/ BaCT. Policy to be reviewed by ACF but not sharing SOP | pending | pending | -: -; Yes: Yes; Yes: Yes; -: -; -: - | CTRNet, NPAAC | No
|  | Templates | 9.3.1 | Cost Recovery Model (previously called Fees - Biospecimen & Data access) | Refer Cost recovery policy - TR-ANZGOG Lab network:V2_Final | 2020-05-24 | Approved | Sept 2020 | See above in lab network section. | pending | pending | -: -; Yes: Yes; Yes: Yes; -: -; -: Yes | INOVATe, kConFab, NSWHSB, APGI, Griffith, Mater Path, TRI, WIMR | Yes
|  | Templates | 9.3.2 | EOI - Biospecimen Resource | V1 | 2018-11-26 | Approved | n/a | Based on INOVATe (WIMR?) docs for NSWHSB grant application. Circulated to S/C at time of grant application | AdF | 2018-12-01 | [9 empty] | WIMR | Yes | bar: - to -
|  | Templates | 9.3.3 | Application Form - Biospecimen Resource | V1 | 2018-11-26 | Approved | n/a | Based on INOVATe (WIMR?) docs for NSWHSB grant application. Circulated to S/C at time of grant application | AdF | 2018-12-01 | [9 empty] | WIMR | Yes | bar: - to -
|  | Templates | 9.3.4 | Reviewer Check Sheet -Biospecimen Resource | V1 | 2018-11-26 | Approved | n/a | Based on INOVATe (WIMR?) docs for NSWHSB grant application. Circulated to S/C at time of grant application | AdF | 2018-12-01 | [9 empty] | WIMR | No | bar: - to -
|  | Templates | 9.3.5 | Amendment/ Notification Form - Biospecimen Resource | V1 | 2018-11-26 | Approved | n/a | Based on INOVATe (WIMR?) docs for NSWHSB grant application. Circulated to S/C at time of grant application | AdF | 2018-12-01 | [9 empty] | WIMR | Yes | bar: - to -
10 | Sustainability and Succession Planning | n/a | 10.1 | Business Plan | FINAL | 2020-07-27 | Approved | 2020-06-01 | CD to work with AE and UW on Business Plan May/June 2020 | pending | pending | -: Yes; Yes: Yes; Yes: Yes; -: -; -: - | Business Strategy plan | No
Note on T24: TR-ANZGOG: RMG members are SC members
Note on M25: TR-ANZGOG: every 2 years or annual?
Note on H35: TR-ANZGOG: AE and AdF signatures on letter required. Notify of change to ANZGOG publication policy not TR-ANZGOG policy
Note on H37: TR-ANZGOG: Notify Anna of minor amendment - omission of 'ficoll' procesing for ascites and submission deadline AE suggested RMG sign off required
Note on H38: TR-ANZGOG: $2K-$3.5K
Note on H39: TR-ANZGOG: combined with CRA price
Note on E48: TR-ANZGOG: include SOP for TR-ANZGOG TMA construction and slide cutting
Note on E68: TR-ANZGOG: Document not required?

## Acronyms
Initials
S/C | TR-ANZGOG Steering Committee
RMG | ANZGOG Research Management Group
CW | TR-ANZGOG Consensus Workshop
CWG | Consent Working Group
LNWG | Lab Network Working Group
DMWG | Data Management Working Group
AE | Alison Evans
ADF | Anna De Fazio
HCB | Hunter Cancer Biobank
NSWHSB | NSW Health Statewide Biobank
NGOR | National Gynae Oncology Registry
JA | John Andrews

## Potential reviewers
Area of Expertise
Discipline | TR-ANZGOG S/C member | ANZGOG Member | External
Legal |  | Alison Choy Flanagan
Governance | Alison Evans (NSW) | Alison Hall, BaCT | ?Tony Penna
Danielle Miller, CTC
Study Coordinator |  | Sue Brew (Newcastle)
Kathryn Jenkins (NSW)
Joanne Youd (WA)
Belinda Egan (NZ)
Med Onc | Phil Beale (NSW) | Yoland Antill
| Alison Davis (ACT) | Yeh Chen Lee (NSW)
| Linda Mileshkin (VIC) | Peey Sei Kok (NSW)
| Michelle Vaughan (NZ) | Tarek Meniawy (WA)
Cath Shannon (QLD)
Michelle Harrison (NSW)
Allison Black (TAS)
Michelle Wilson (NZ)
Pathologist | Lyndal Anderson (NSW) | Deb Smith (QLD) | Adeline Tan (WA)
|  | Rohan Lourie (QLD) | Kerryn Ireland-Jenkin (VIC)
Chris Carter (SA)
Surgeon | Alison Brand (NSW) | Paul Cohen (WA)
Rhonda Farrel (NSW)
Lew Perrin (QLD)
Peter Sykes (NZ)
Operations | John Andrews (NSW) | Katrina Diamante (NSW)
Hannora Jurkovic (NSW)
Ethics | Phil Beale (NSW) | Haryana Dhillon (NSW)
Sarah York (NSW)
Pure Science researcher | Anna de Fazio (NSW) | John Hooper (QLD)
| Pam Pollock (QLD) | Caroline Ford (NSW)
| David Bowtell (VIC) | Nicki Meagher (NSW)
Amanda Spurdle (QLD)
Clinician Researcher | Clare Scott (VIC)
Biobanking/ Translational Research |  | Nadia Traficante (VIC)
Sonia Yip (NSW)
Cath Kennedy (NSW)
Sanela Bilic (WA)
Data management |  | Penny Webb (QLD) | Mark McLean (NSW)
Pamela Provan (NSW)
Susan Ramus (NSW)
Consumer | Karen Livingstone (VIC) | Wanda Lawson (QLD)
Kathryn Cornthwaite (QLD)
Statistician |  | Val Gebski
Liz Barnes